### 2008-2009

### Accessibility Plan

### for

#### Nipissing University

#### Updated September 2008

Submitted by
Dan Pletzer, Chair
Accessibility Planning Committee

This document is available in alternative format

#### CONTENTS

Page

EXECUTIVE SUMMARY 								   3

Nipissing University’s Accessibility Plan 					   4

SECTION ONE

Accessibility Planning In Action

1.1	Mandate of the Accessibility Planning Committee		   5

1.2	Nipissing University Accessibility Planning Committee

2008-2009								   5

SECTION TWO

2007 - 2008 Accessibility Plan Update
	2.1	Update on previous year’s barrier identification methods	   7

2.2	Update on previous year’s barrier prevention and removal objectives								   8

SECTION THREE

2008 – 2009 Accessibility Planning Initiatives

3.1	Methods to be used for identifying barriers in 2008-2009	  11

3.2	Barrier prevention and removal objectives for 2008-2009	  11

3.3.	Customer Service							  12

3.4.	Transportation							  13

3.5	Information and Communications					  14

3.6	Built Environment							  15

3.7	Employment								  17

#### 2008-2009 Accessibility Improvement Priorities				  18

Review and Monitoring Process						  18

Communication of the Plan							  18

Executive Summary

Barrier identification, prevention and removal are ongoing processes.  Nipissing University began its accessibility planning process in 2002-2003 and made public its first annual Accessibility Plan in September 2003.  Updated reports on the status and progress of the goals and objectives of the previous years’ plans have been produced annually.  This current 2008-2009 Accessibility Plan provides details on the progress of previously stated barrier prevention and removal objectives, plus it describes new barriers which have been identified during the past year.

Five Standards Development Committees have been established by legislation set out by the Accessibility for Ontarians with Disabilities Act (AODA 2005).  Through the mandate of the Accessibility Directorate of Ontario, Ministry of Community and Social Services, there are five standards in different stages of development and/or implementation:

- Customer Service Accessibility Standard

- Accessible Transportation Standard

- Accessible Information and Communications Standard

- Accessible Built Environment Standard

- Employment Accessibility Standard

The first set of standards - Customer Service Accessibility Standard came into effect as law on January 1, 2008.  Businesses and organizations in Ontario that provide goods or services to the public are now legally required to make their customer service operations accessible to persons with disabilities.  This includes universities.  Achieving and delivering accessible customer services will be done by identifying and removing barriers to customer service in such areas as operational practices, policies and procedures, communications and staff training.  This remains one of the University’s priorities as we move forward into 2008-2009 and plan to meet and exceed the Customer Service Accessibility Standard compliance requirements as of January 01, 2010.

Originally framed within the 7 general categories initially set out by the Council of Ontario Universities ODA Task Force in 2002, Nipissing University’s previous annual accessibility plans have followed this framework for the identification of accessibility areas to be reviewed.  For 2008-2009, this framework has been transformed bringing it into alignment with the current five AODA Accessibility Standards.  As such, the following key objectives of the 2008-2009 plan are:

- to report on the evaluation and prioritization of the recommendations of previous Accessibility Plans in conjunction with short and long range planning and financing objectives;

- to report on opportunities provided for students, staff, faculty and visitors to participate in the ongoing barrier identification process;

- to report on the progress being made in areas of compliance with the Customer Service Standards and future AODA Standards as these become established.

#### Nipissing University’s Accessibility Plan

#### This 2008-2009 report constitutes an addendum to the institution’s Accessibility Plan which was originally established in September 2003 and updated annually in September 2004, 2005, 2006 and 2007.  As such, it:

- reviews the commitments and progress that Nipissing University has made to identify, remove and prevent barriers to persons with disabilities in its facilities, policies, programs, practices and services

- provides updates on the processes by which Nipissing University will use to identify barriers to people with disabilities

- describes the measures Nipissing University will take in the coming year, or years, to remove and prevent barriers to persons with disabilities

- examines the institution’s progress on barrier identification, prevention and removal strategies which are now aligned with the current five AODA Accessibility Standards either in implementation or in development.

#### SECTION ONE

#### Accessibility Planning In Action

1.1	Mandate of the Accessibility Planning Committee

Established in March 2003 the mandate of the Nipissing University Accessibility Planning Committee is to:

- Conduct inquiries regarding potential and actual barriers to people with disabilities in all facilities, regulations, policies, programs, practices and services offered by Nipissing University

- Identify facilities, regulations, policies, programs, practices and services that cause or may cause barriers to people with disabilities

- Prioritize and specify barriers that will be removed or otherwise modified in the coming year within the limits of the financial and human resources available

- Describe how these barriers will be removed or prevented

- Prepare an annual report on these activities

- Make an Annual Accessibility Plan available to the public

##### 1.2	Nipissing University Accessibility Planning Committee 2008-2009

The following representatives of the university community comprise the Nipissing University Accessibility Planning Committee for 2008-2009:

| Planning Committee Member | Department | Contact Information |
| --- | --- | --- |
| Darlene Brackenreed | Professor – Faculty of Education | Ext 4502 |
| Al Carfagnini | Executive Director, Student Affairs | Ext. 4278 |
| Peggy Cook | Manager of Administrative and Facility Services Office of the Vice-President, Finance & Administration | Ext. 4288 |
| Craig Cooper | Dean – Faculty of Arts and Science | Ext. 4290 |
| David Cotie | Director College Facilities Canadore College | Ext. 5502 |
| Ken Crocker | Executive Director, University Advancement | Ext.4426 |
| Daralynn D’Angelo | Learning Strategist – Disability Services | Ext. 4235 |
| Jack Jones | Office of Instruction and Learning | Ext. 4281 |
| Bob Keech | Technology Services - Chief Information Officer | Ext. 4353 |
| Brian Nettlefold | Executive Director – Library Services | Ext. 4220 |
| Dan Pletzer (Chair) | Manager – Counselling and Disability Services | Ext. 4493 |
| Peter Ricketts | Vice President, Academic & Research | Ext. 4254 |
| Katrina Srigley | Professor – Faculty of Arts & Science | Ext. 4503 |
| Connie Vander Wall | Associate Vice-President, Human Resources | Ext. 4497 |
| Ian Wassink | Vice-President Internal - Nipissing University Student Union | Ext. 4409 |
| Ron Wideman | Dean (interim) – Faculty of Education | Ext. 4268 |
| Shanon Wilson | Director of Facility Services, Capital Projects and Construction | Ext 4842 |

#### SECTION TW0

2007 - 2008 Accessibility Plan Update

An update on the actions and measures set out in the 2007-2008 Accessibility Plan to identify, prevent and remove barriers for persons with disabilities when accessing the University’s facilities, programs and services is presented below.

  - Update on previous year’s barrier identification methods

The table below specifies each barrier identification method that was implemented during the 2007-2008 academic year and it indicates the current status of the specific barrier identification method.

| Methodology | Status |
| --- | --- |
| Incoming Student Voluntary Self-Identification form | Completed and Ongoing -- As students register, this information is provided to the Learning Strategist in Disability Services |
| Consultation with departmental representatives according to the University Accessibility Planning checklist prepared by the COU AODA Planning Committee | Completed and Ongoing – Under the mandate of the Nipissing University Accessibility Planning Committee |
| Joint accessibility planning with Canadore College | Completed and Ongoing – Accessibility Plans continue to be shared between institutions |
| Program Evaluation and Barrier Identification Survey for Students Disabilities | Completed and Ongoing – Survey was distributed to students in April 2008. Responses were summarized and presented to the Accessibility Planning Committee. Recommendations for new or additional barrier removal priorities are included in the barrier removal/prevention section of this report. |
| Faculty and Staff survey on barriers to persons with disabilities | Completed and Ongoing – Survey was distributed to all faculty and staff in March 2008. Responses were summarized and presented to the Accessibility Planning Committee. Recommendations for new or additional barrier removal priorities are included in the barrier removal/prevention section of this report. |
| Campus Safety Audit | Completed and Ongoing – Representatives from Disability Services participate an annual audit of physical facilities. An updated report was completed in Fall 2008 noting areas where improvements are required and a committee updates and prioritizes the activity list of improvements. |
| Library Survey | Completed and Ongoing -- A library user survey provides persons with a disability with an opportunity to identify barriers to accessing library facilities. |
| Focus Group on disability barrier identification | Not completed in 2007-2008; plan to complete at least one focus group session 2008-2009. |

2.2	Update on previous year’s barrier prevention and removal objectives

The following barrier prevention and removal objectives were presented as “in progress” in the September 2007 Accessibility Plan for Nipissing University.  This table provides a brief description and the current status of previously identified objectives.

| Previously Identified Objective | Progress & (status) |
| --- | --- |
| A partial accessibility audit was completed in 2005-2006, a report on findings and recommendations was submitted to the chair of the Accessibility Planning Committee | Previous reports show items which have been completed; incomplete items are in progress and are prioritized as set out in the ongoing barrier removal plan (ongoing) |
| A draft Faculty Guide was developed during the summer of 2007, as part of the Summer Transition Program for students with disabilities. | Production and publication of a Student Guide was completed in 2008; the Faculty Guide is not yet published (in progress) |
| Users have recommended having baskets and small carts available. | Carrying baskets and a book cart are available for library patrons upon request (completed) |
| Survey faculty, staff and students to identify barriers associated with web-based instructional technology | The following question is included in surveys of students, faculty and staff: “Please identify any modifications or improvements that you think needs be made to instructional / learning environments at Nipissing University so that the needs of persons with disabilities can be better met” (completed) |
| Complete an inventory of current parking allocations for persons with disabilities and review with Parking and Security Services utilization patterns and designated locations. | Inventory report not completed; send reminder to Parking and Security Services in 2008-2009 (in progress) |
| Conduct a barrier-free audit of Nipissing’s external and internal physical facilities Identified barriers will be considered as part of the ongoing facilities renewal budget process. | The feasibility of renovating a previously modified townhouse residence was completed in 2008. (completed) All future retrofits will be prioritized based on the recommendations of the accessibility planning committee. (ongoing) |
| Some emergency phones continue to have access barriers and will remain as an item requiring attention. | Improvements have been completed at some locations; item has been noted for 2008-2009 campus safety audit. Re-evaluate in 2008-2009 (partially completed and in progress) |
| Hand rails are needed along staircases in some lecture halls; refer this matter to Physical Plant for evaluation and remedial action plan | Item to be referred to Capital Projects and Construction for evaluation and report in 2008-2009. (in progress) |
| Previously Identified Objective | Progress & Status |
| Emergency Evacuation: Ongoing awareness and procedures for assisting persons with physical and sensory disabilities has been requested in 2007-2008. | Item to be referred to Health and Safety for action in 2008-2009 (in progress) |
| Conduct an audit and provide recommendations for directional signage for elevators in the main building | Audit of directional signage to be completed in 2008-2009. Include costs in 2009-2010 budget submission. (in progress) |
| Explore possible service counter solutions, provide recommendations, and prioritize within institutional budgets | Accessible condiment counters are reported as included in the 2008 renovations in the cafeteria. Re-evaluate status and report. (in progress) |
| Recommend lowering dispensing machines in accessible washrooms Recommend lever handles be installed on washroom doors at Muskoka campus | Re-audit and final report on accessible washroom facilities not complete. Follow up in 2008—2009 and report. Schedule accessibility audits of new and renovated construction projects of both Regional Campuses (Muskoka and Brantford) in 2008-2009 and report. (in progress) |
| Lack of a dedicated rest area in the university for individuals living off-campus; identify the need for this space in future physical resources planning | Future space planning is in progress and designated rest area(s) will be identified. (in progress) |
| Evaluate and improve access to the platform level of B200 and B201, including corridors and doorways | Include these areas in a future joint physical accessibility audit and report with Canadore College (in progress) |
| Evaluate hallway between Student Services and Brown Lounge which is reported as not being “wheelchair friendly”. | Hallway has a 50” path of travel and 38” one door passage, meeting the minimum standard. Hallway has been closed at one end and is not a designated high-traffic thoroughfare route, providing access to local offices only. Alternative directional signage is not required. (completed) |
| Improve availability of learning strategists to facilitate an open door policy on service, rather than by appointment | Trained peer mentors have been introduced to compliment the services provided by the learning strategists. Monitor staff caseloads and evaluate future staffing requirements as part of the Department’s planning process. (ongoing/completed) |
| Raise awareness in the campus community regarding use of perfumes/scents and their impact on persons with environmental sensitivities | ‘No Scents’ policy is in place for tests/exams. Posters have been developed and strategically located to assist in awareness raising efforts. (ongoing/completed) |
| Previously Identified Objective | Progress & Status |
| Assigned seating, also seating accommodation, is needed for students with disabilities who require accommodations in the classroom | Accommodated seating is included in the Accommodation Checklist which is reviewed with each student during their Individualized Education Planning meeting. Advise Learning Strategists of this comment. (completed) |
| Improve access to classroom PowerPoint presentations, lecture notes | Provision of slide presentations and lecture notes are encouraged as part of faculty training in the use of instructional technology and concepts of universal instructional design; discretion remains within the prevue of the professor, if not an accommodation issue. Students may request accommodation in this area through their designated learning strategist. (ongoing/completed) |
| Test writing in Student Affairs is uncomfortable – monitoring, number of students, full sized keyboards | Renovations in 2008 included an accommodated testing centre providing 8 additional test/exam writing workstations featuring accessible furniture and technology. (completed) |
| Make televisions in classrooms work for students who can’t see the overhead | Encourage and support professors to use CCTV’s when using main projection screen and if not working, request repair. UTS will audit CCTV status in all classrooms where these are used. (completed) |
| Bursary for Students with Disabilities to purchase assistive technology is dependent upon OSAP eligibility | This is a MTCU policy. Continue to recommend de-coupling of BSWD and OSAP (ongoing/completed) |
| Cafeteria does not publish food ingredients re: allergies | Memorandum to be provided to the food services advising of this concern, requesting possible solutions/report (in progress) |

SECTION THREE

2008 - 2009 Accessibility Planning Initiatives

3.1	Methods to be used for identifying barriers in 2008 – 2009

The following chart sets out the university’s commitment to the methods that will continue to be used or be introduced in 2008-2009:

| Method | Description |
| --- | --- |
| Continuation of the Accessibility Planning Committee | The Accessibility Planning Committee which represents the broader interests of the university community will assess and recommend current measures to identify, remove and prevent barriers and to coordinate campus-wide awareness initiatives. |
| Accessibility audit of external and internal facilities, services and programs. | In collaboration with Canadore College, community agencies and persons with disabilities, ongoing accessibility audits and safety audits of facilities, services and policies will occur. |
| Survey of Students with Disabilities | A barrier-identification survey will continue to be made available to students with disabilities during the 2008-2009 academic year. |
| Survey of Faculty and Staff | A barrier identification survey will be distributed to all employees of Nipissing University during the 2008-2009 academic year. |
| Library user feedback questionnaire | An accessible survey which includes specific questions pertaining to disability access will continue to be available to all patrons in an accessible area near the main entrance to the Library and on-line. |
| Focus Groups | A barrier-identification focus group will be conducted during 2008-2009. |

3.2	Barrier prevention and removal update for 2008-2009

Using the Accessibility Directorate’s five currently specified Accessibility Standards, these areas have been adopted as the categories under which barriers have been identified.

The barrier identification process used to create the current list of objectives for 2008-2009 relies on the results of surveys, voluntary identification of barriers by staff and faculty as well as information provided by individual members of the Accessibility Planning Committee, including collaboration with the Canadore College Accessibility Plan.

A summary of newly identified barriers is presented in the remainder of this section under items 3.3 to 3.7.

3.3	Customer Service

| Areas of the University Reviewed for Accessibility | Barriers Identified as of Sept 2008 | Strategies to Remove & Prevent Barriers | Responsibilities & Timeline |
| --- | --- | --- | --- |
| AODA Customer Service Standard | Staff training and awareness initiatives indentified in the Customer Service Standard | Develop staff training and awareness initiatives | Human Resources Department in collaboration with the Nipissing University Accessibility Planning Committee (2008-2009) |
| AODA Customer Service Standard | Policy and procedures | Using resources being made available to the University, set out a guide to assist individuals and departments to review existing policy and procedures for compliance | Nipissing University Accessibility Planning Committee (2008-2009) |

3.4	Transportation

| Areas of the University Reviewed for Accessibility | Barriers Identified as of Sept 2008 | Strategies to Remove & Prevent Barriers | Responsibilities & Timeline |
| --- | --- | --- | --- |
| AODA Accessible Transportation Standard | None identified in 2007-2008 | Communicate the progress of the development of the Accessible Transportation Standard and its future application to stakeholders within the university community | Nipissing University Accessibility Planning Committee (2008-2009) |

3.5		Information and Communications

| Areas of the University Reviewed for Accessibility | Barriers Identified as of Sept 2008 | Strategies to Remove & Prevent Barriers | Responsibilities & Timeline |
| --- | --- | --- | --- |
| Application of the proposed Information and Communication Standards in the university community | No specific barriers identified in 2007-2008 | Communicate the progress of the development of the Information and Communications Standard and its future application to stakeholders within the university community | Nipissing University Accessibility Planning Committee (2008-2009) |

3.6		Built Environment

| Areas of the University Reviewed for Accessibility | Barriers Identified as of Sept 2008 | Strategies to Remove & Prevent Barriers | Responsibilities & Timeline |
| --- | --- | --- | --- |
| Pedestrian Routes (Doors, Ramps, Stairs, Lighting, Walls, Corridors, Elevators) | Automatic door opener to Human Resources Department | Present to Accessibility Planning Committee for prioritization | Nipissing University Accessibility Planning Committee (2008-2009) |
| Pedestrian Routes (Doors, Ramps, Stairs, Lighting, Walls, Corridors, Elevators) | Automatic door opener to Advancement Office | Present to Accessibility Planning Committee for prioritization | Nipissing University Accessibility Planning Committee (2008-2009) |
| Pedestrian Routes (Doors, Ramps, Stairs, Lighting, Walls, Corridors, Elevators) | Monastery Hall Washroom doorway reported to swing outward and requires automatic door opener | Refer to Capital Projects and Construction for evaluation and report | Nipissing University Accessibility Planning Committee (2008-2009) |
| Pedestrian Routes (Doors, Ramps, Stairs, Lighting, Walls, Corridors, Elevators) | Barriers associated with accessible sidewalk access route between Governor’s House and main campus building | Re-assess accessible sidewalk access route safety and maintenance issues between Governor’s House and main campus building | Nipissing University Accessibility Planning Committee in consultation with Capital Projects and Construction (2008-2009) |
| Capital Projects and Construction | Include accessibility planning for new science wing and e-learning centre | Draft proposed policy for review and approval by Board of Governors Plant and Property Committee | Nipissing University Accessibility Planning Committee (2008-2009 |
| Pedestrian Routes (Doors, Ramps, Stairs, Lighting, Walls, Corridors, Elevators) | Identification of stairway approaches and stairway steps for person with vision-related disabilities | Request that all stairwells and steps be appropriately marked and identified | Nipissing University Accessibility Planning Committee in consultation with Capital Projects and Construction; Health and Safety (2008-2009) |
| Pedestrian Routes (Doors, Ramps, Stairs, Lighting, Walls, Corridors, Elevators) | Emergency alarms for persons who are Deaf/deafened | Evaluate and report on emergency alarm improvements for persons who are Deaf/deafened | Nipissing University Accessibility Planning Committee in consultation with Capital Projects and Construction; Health and Safety (2008-2009) |
| Pedestrian Routes (Doors, Ramps, Stairs, Lighting, Walls, Corridors, Elevators) | Condition and cleanliness of Elevator in B section | Recommend repainting interior of B section elevator | Nipissing University Accessibility Planning Committee (2008-2009) |

3.7	Employment

| Areas of the University Reviewed for Accessibility | Barriers Identified as of Sept 2008 | Strategies to Remove & Prevent Barriers | Responsibilities & Timeline |
| --- | --- | --- | --- |
| AODA Customer Service Accessibility Standard | Compliance with staff training and awareness of Customer Service Accessibility Standard | Provide training within the university community regarding compliance requirements as per the AODA Customer Service Accessibility Standard | Nipissing University Accessibility Planning Committee with the Human Resources Department (2008-2009) |
| AODA Accessible Employment Standard | None identified in 2007-2008 | Communicate the progress of the development of the Accessible Employment Standard and its future application to stakeholders within the university community | Nipissing University Accessibility Planning Committee (2008-2009) |

#### 2008-2009 Accessibility Improvement Priorities

#### Considering safety issues as the primary factory, followed by customer service compliance requirements, the following barrier identification, prevention and removal initiatives were endorsed by the Nipissing University Accessibility Planning Committee for 2008-2009:

#### Improve identification of stairway approaches and risers;

#### Request proposals to install safety handrails in H100 lecture halls;

#### Draft and promote awareness of an emergency evacuation procedure for persons with mobility disabilities;

#### Request proposals to improve access to emergency phones;

#### Assess outstanding safety and accessibility issues related to the sidewalk between Governor’s House and the main campus building; budget for recommended improvements;

#### Install automatic door opener in Human Resources area;

#### Prepare a Customer Service Compliance plan for January 2010.

#### Review and Monitoring Process

The Planning Committee will meet as needed at the call of the Chair to review the action plan and update progress on the plan. Members of the committee will encourage staff and faculty members, either through personal contacts or by e-mail, about the role of the Accessibility Planning Committee and will seek input regarding the objectives of the plan.

#### Communication of the Plan

A copy of this plan is available on the University Web site at http://www.nipissingu.ca, and from the Office of the President or Vice President Administration and Finance.  The report is also available on CD Rom and in large print format.  A copy of the report will be transcribed into Braille format, upon request.  Inquiries regarding Nipissing University’s 2008-2009 accessibility planning process may be directed to the Accessibility Planning Committee Chair in the following ways:

Mail:	Dan Pletzer

Manager of Counselling and Disability Services

Nipissing University

100 College Drive, North Bay, Ontario

P1B 8L7

Telephone:  	(705) 474-3450 ext 4493

TTY:  		(705) 474-8797

Fax:		(705) 495-2850

Email:  danp@nipissingu.ca